## Project Details
Project Details
project Name | Shopify Addon Purchase Testing
Website URL | https://spicedemo.myshopify.com/
Product URL | https://spicedemo.myshopify.com/products/military-watches-mens-quartz-watch
Testing Type | Manual Testing
objective | Test addon purchase with main product
Assign Date | 2026-04-17
Assign By
Cross Browsing Testing | Chrome ¦ Firefox

## Test Scenarios
Test Scenarios
Scenario ID | Test Scenario Data | Test Scenario Title | Preconditions | Expected Result | Actual Result | Comments
TS_01 | Open Product URL | To verify that user able to open product URL | Product page open | Open product URL successfully | Product page will be open seccessfully | Working as expected
TS_02 | Add main product to ATC | To verify that user can add main product to ATC | Add product to ATC | main product add successfully to ATC | Main product added to ATC | Working as expected
TS_03 | Add main product + 1 addon to ATC | To verify that user can add main product + 1 addon to ATC | Add product +1 addon to ATC | product + 1 addon added succesfully to ATC | Poduct + addon added To ATC | Working as expected
TS_04 | Add multiple addons with a product | To verify that user can add more than 1 addons with a product | Add multiple addons | More than one addon not selected | Multiple addons will be selected | Difference occure
TS_05 | Check products on ATC section | To verify that added ATC product visible or not | Check ATC section | Product will be visible on ATC section | Product is visible on ATC section | Working as expected
TS_06 | check product pricing | To verify that product pricing will be same when added to ATC | Check Pricing on ATC | Price will be same on ATC section | pricing is same on ATC | Working as expected
TS_07 | Check unavailable addons | To verify that unavailable addons aren't added to ATC | Unavailable Addons | Unavailable addons not added to ATC or Show restrictions | Unavailabe addons added to the ATC and not showing any restriction | Difference occure
TS_08 | Check buy now section | To verify that buy now section is working | Check buy now | Buy now section working Well | Buy now section is working good | Working as expected
TS_09 | Check Remove Functionality | To verify that ATC remove items functionality is working | Remove item functionality | Remove item button can remove the items properly | Remove items button works nicely | Working as expected
TS_10 | Check multiple clicks on ATC | To verify that multiple clicks on ATC button for same product | Multiple clickes on ATC | Multiple clicks not add same product after 1 time added to ATC | Multiple clicks added the same product multiple times To ATC | Difference occure
TS_11 | Cross browser check | To verify that product URL work same on all browsers | Cross browsing | URL and UI-UX works well in all browsers | URL and UI -UX works Same on all browser | Working as expected
TS_!2 | Check responsiveness for devices | To verify that Responsiveness of the website for devices | Responsiveness Ui | Website should work well in all devices | Website works properly in all devices | Working as expected

## Test Cases
Test Cases
Test Case ID | Test Case Description | Preconditions | Test Data | Steps | Expected Result | Actual Result | Status | Comments
TC_01 | Buy main product with one add-on | Product page is loaded | 1 main product + 1 addon | Open product page; Select an addon; Click Add to Cart; Proceed to checkout | Product + selected addon added successfully | Product and addon added correctly | Pass | Working as expected
TC_02 | Buy main product without selecting addon | Product page is loaded | No addon | Click Add to Cart without selecting addon | main product added | Main product added without addon | Pass | Addon is optional
TC_03 | Select multiple addons | Product page with multiple addons | Addon A + Addon B | Try selecting more than one addon; Click Add to Cart | Either only one selectable OR error shown | Multiple addons got selected and added | Fail | BUG: System allows multiple addons
TC_04 | Change addon before adding to cart | Product page loaded | Select addon A change Addon B | Select addon A; Change to addon B; Click Add to Cart | Only addon B added | Only addon B added | Pass | Correct Changing
TC_05 | Add to cart without clicking addon properly | Product page loaded | Addon | Quickly click Add to Cart without proper selection | Addon can not be selected | Addon not added, only product added | Pass | System ignores incomplete selection
TC_06 | Verify cart items | Product + addon added | Product + addon | Open cart page | Cart shows main product and only 1 addon | Cart shows product + addon correctly | Pass | Cart working fine
TC_07 | Update quantity in cart | Cart has product + addon | Increase main product qty. | Increase quantity in cart | Addon behaves correctly | Addon quantity also increases automatically | Pass | Working as expected
TC_08 | Remove addon from cart | Cart has product + addon | Addon | Remove addon from cart | Only addon removed | Addon removed successfully | Pass | Works as expected
TC_09 | Remove main product | Cart has product + addon | Product | Remove main product | Addon should also be removed | Addon not removed | Fail | BUG: Addon not remove when product remove from ATC
TC_10 | Proceed to checkout | Cart has product + addon | Checkout page | Click checkout | Both product + addon visible | Both visible in checkout | Pass | Working fine
TC_11 | Verify pricing calculation | Cart ready | Product + addon price | Check total amount | Total = product + addon price | Total calculated correctly | Pass | No pricing issue
TC_12 | Try adding addon without main product | Add addon without product | Addon | Attempt to add addon alone | System should not allow | Addon cannot be added alone | Pass | Restriction working
TC_13 | Browser refresh after selection | Addon selected | Addon | Refresh page | Selection retained OR reset properly | Selection gets reset | Pass | Working as expected
TC_14 | Multiple clicking Add to Cart | Product page loaded | Addon | Click ATC multiple times quickly | No duplicate entries created | Duplicate items added | Fail | BUG: Duplicate items added at ATC when clicking multiple times on ATC
TC_15 | Mobile responsiveness | Mobile device | Addon | Test on mobile | Addon selection works properly | UI Issue | Pass | Minor UI issue
TC_16 | Different browsers | Multiple browsers | Addon | Test on Chrome, Firefox | works same on all browsers | Works fine on all browsers | Pass | Cross-browser compatible
TC_17 | Add multiple main products | Cart available | Multiple products | Add multiple main products | Each product allows only 1 addon | Each product allows one addon | Pass | Working as expected
TC_18 | Addon out of stock | Addon unavailable | Try to select unaailable addon | Select unavailable addon; Click add to cart | Unavailable Addon is not added to ATC | Unavailable item is still selected | Fail | BUG: Inventory bug or UX Problem

## Bug Reporting
Bug Reporting
Bug ID | Test Case | Issue | Severity | Priority
BUG_01 | TC_03 | Multiple add-ons allowed | High | High
BUG_02 | TC_09 | Add-on not removed with product | Critical | High
BUG_03 | TC_14 | Duplicate items on multiple clicks | Medium | Medium
BUG_04 | TC_18 | Out-of-stock add-on selectable | High | High
project Name | Shopify Addon Purchase Testing
Website URL | https://spicedemo.myshopify.com/
Product URL | https://spicedemo.myshopify.com/products/military-watches-mens-quartz-watch
Testing Type | Manual Testing
objective | Test addon purchase with main product
Cross Browsing Testing | Chrome ¦ Firefox
Responsiveness Test | Laptop ¦ Mobile